## Current Iteration
|  | Iteration Number: |  |  |  | 0
|  | Expected Total effort: |  |  |  | 35
|  | Days In Sprint: |  |  |  | 17
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Updated BRD and Management Plan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 |  |  |  | 0 | 100%
Home Page: Create Mock Up for Home Page | 5 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 100%
Your Pets Page: Create a Mock Up for Your Pets Page | 3 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 100%
Your Pets Page: Create a Mock Up for Add Pets Page | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 100%
Architecture and Design | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  |  | 0 | 100%
Project Requirements Document (PRD) | 13 | 0 | 2 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 |  |  |  | 0 | 100%
0
0
0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 35 | 33 | 31 | 29 | 26 | 23 | 20 | 17 | 16 | 14 | 12 | 10 | 8 | 6 | 5 | 4 | 2 | 0 | #N/A | #N/A | #N/A | 0 | 100%
Ideal Trend | 35 | 32.9412 | 30.8824 | 28.8235 | 26.7647 | 24.7059 | 22.6471 | 20.5882 | 18.5294 | 16.4706 | 14.4118 | 12.3529 | 10.2941 | 8.2353 | 6.1765 | 4.1176 | 2.0588 | 0 | - | - | -